## Sheet1
Process: Curriculum Design and Review
Purpose: Effective curriculum design and review for academic programmes in JOOUST
Output: Accredited programmes for implementation
| ACTIVITIES | Inputs | RISK | RISK LEVEL | RISK IMPACT | MITIGATION | OPPORTUNITY | ACTIONS
1 | Collection and collation of data | Data Collection Tools | · Inappropriate tools | low | High | Verification and validation of tools |  | Competent staff
|  |  | · Inappropriate methods |  |  | Out sourcing and capacity building | · Use of technology | Capacity building
|  |  | · Quorum hitch |  |  | Use of technology | ·
|  |  | · Non- responsiveness of interested parties |  |  | Declaration of conflict of interest
|  |  | · Conflict of Interest |  |  | Prepared Action Plans
|  |  | · Time Constraints |  |  | Making budgetary provisions Prudent resource utilization
· Inadequate expertise
· Inadequate resources
· Budgetary Constraints
2 | Data Analysis | Data Analysis tools | · Time Constraints | High | High | Prepared Action Plans | Use of modern Technology
|  |  | · Inadequate expertise |  |  | Capacity buiding
· Inadequate resources
· Budgetary Constraints
3 | Develop /review draft programme | Curriculum Programme expertise |  | High | High
|  |  | inadequate resources |  |  | Sourcing and capacity building | Use of modern Technology
|  |  | budgetary contsraints |  |  | Prepared Action Plans | Virtual programmes delivery modes with e-learning
|  |  | Time constraints |  |  | Civic education/Sensitization | Demand for consultancy
|  |  | Irrelevance of the curriculum |  |  |  | Government support
|  |  | Political exbidience |  |  |  | Knowledge based economy
Lack of participation
4 | Approval of programme by relevant committees | Competent staff | Non-adherance to CUE requirements | High | High
|  | Resources | Noncompliance to statutory and regulatory requirements |  |  | Sourcing and capacity building | Use of modern Technology
[6 empty] | Prepared Action Plans | Virtual programmes delivery modes with e-learning
[6 empty] | Civic education/Sensitization | Demand for consultancy
Government support
Good will from local and national leaders
5 | Submission for accreditation | Resources | Non-adherance to CUE requirements | High | High | Adherance to CUE requirements | Market driven programmes
|  | Competent staff | Noncompliance to statutory and regulatory requirements |  |  | Compliance to statutory and regulatory requirements | supportive governance and administrative leadership
Competent staff
5 | Implementation of accredited programme | Resources | Non-adherance to CUE requirements | High | High | Prepared action plan | Intrested parties goodwill
|  | Competent staff | Noncompliance to statutory and regulatory requirements |  |  |  | Increasing number of trained personnel in the job market
|  | Good will from Intrested parties |  |  |  |  | Public-Private Partnership (PPP)
demand for higher, continuing and professional education
Virtual programmes delivery modes with e-learning
Knowledge based economy
Availability scholarships/sponsorships
Use of mordern technology
Government funding
Market driven programmes
University - industry linkages
Good labor relations